## Full Timeline
This document is Vermont Medicaid's draft Home- and Community-Based Services (HCBS) Conflict of Interest (COI) corrective action plan (CAP). The Centers for Medicare and Medicaid Services (CMS) is currently reviewing this draft CAP. For more information, please visit The Vermont HCBS COI website at https://dvha.vermont.gov/global-commitment-to-health/conflict-of-interest-home-and-community-based-services.
The activities in this workplan apply to all five Vermont HCBS programs unless noted otherwise.
| Sept. 2022 | Oct. 2022 | Nov. 2022 | Dec. 2022 | Jan. 2023 | Feb. 2023 | Mar. 2023 | April 2023 | May 2023 | June 2023 | July 2023 | Aug. 2023 | Sept. 2023 | Oct. 2023 | Nov. 2023 | Dec. 2023 | Jan. 2024 | Feb. 2024 | Mar. 2024 | April 2024 | May 2024 | June 2024 | July 2024 | Aug. 2024 | Sept. 2024 | Oct. 2024 | Nov. 2024 | Dec. 2024 | Jan. 2025 | Feb. 2025 | Mar. 2025 | April 2025 | May 2025 | June 2025 | July 2025 | Aug. 2025 | Sept. 2025 | Oct. 2025 | Nov. 2025 | Dec. 2025
1: Stakeholder Engagement
Develop stakeholder engagement plan that maps out key internal and external stakeholders and when/how each stakeholder will be involved.
Establish advisory stakeholder group(s) consisting of consumers, providers, families, guardians, advocates, and other groups. Convene regularly for input/working sessions and regular updates.
Develop and provide diverse and accessible methods of informing/engaging stakeholders (webinars, letters, brochures, surveys, interviews, regional meetings etc.). Offer safe spaces for input.
2: HCBS System Assessment
Review available data (NCI, SAMS, claims, etc.) regarding eligibility, assessment, person-centered-plan development, and HCBS delivery. Collect other data as recommended by the TA contractor.
Map current eligibility, assessment, person-centered plan development, and service system.
Assess the extent to which current benefit structures meet the needs of program participants. For example, delivery of HCBS vs rehab services.
Assess workforce capacity using tool(s) and strategies recommended by the TA contractor.
Inventory all care coordination/case management and assessment activities across AHS programs.
3: Establish New Eligibility, Assessment, Person-Centered-Plan Development, and Service Delivery Systems
Determine desired assessor and case manager qualifications, roles, and responsibilities.
Establish target caseload for assessors/case managers by program.
DECISION POINT: Impact analysis of independent assessment/case management options: should assessment or case mgmt be provided by the State, or procure for these services?
4: Reimbursement Methodologies and Financial Modeling
Assess financial impact of delivering assessment or case management via the State vs procure for these services.
Revise existing reimbursement methodologies/rates and value-based payment models based on new scope of work.
Establish reimbursement methodology for new assessment and/or case management entity(ies).
5: Statute, Policy, and Manual Review and Updating
Identify necessary statute changes and amend statutes.
Identify necessary rule changes and amend rules.
Identify necessary manual changes and amend manuals.
6: Quality Management System
Develop provider standards that address quality and performance measures for assessment and case management entities.
Develop quality review protocol for new assessment and case management entities. Modify quality review protocols for current service providers as needed.
Modify critical incident reporting (CIR) protocols.
7: Implementation Planning
Health care system integration planning.
Determine how, when, and which individuals will be transitioned to independent case management for assessment and person-centered planning.
Develop process flows for eligibility, assessments and reassessments, case management, service coordination, and service delivery.
Develop training and orientation plan for providers, assessors, case managers, consumers, families, advocates, community partners, etc.
As needed, establish a policy to identify areas of the state or scenarios that may be eligible for the only willing and qualified provider exemption.
Develop and execute selection process (e.g., request for proposals, certification process, provider enrollment, etc.) for entity(ies) to conducting assessments and/or case management.
Develop readiness review plan.
8: Implement New Eligibility, Assessment, Person-Centered-Plan Development, and Service Delivery Systems
Conduct readiness review
Update MMIS based on new billing/reimbursement structures, quality, and financial reporting.
Provide training and orientation to providers, assessors, case managers, consumers, families, advocates, community partners, etc.
Transition individuals to new assessment and case management system(s).

## 2022 Timeline
| Sept. 2022 | Oct. 2022 | Nov. 2022 | Dec. 2022
1: Stakeholder Engagement
Develop stakeholder engagement plan that maps out key internal and external stakeholders and when/how each stakeholder will be involved.
Establish advisory stakeholder group(s) consisting of consumers, providers, families, guardians, advocates, and other groups. Convene regularly for input/working sessions and regular updates.
Develop and provide diverse and accessible methods of informing/engaging stakeholders (webinars, letters, brochures, surveys, interviews, regional meetings etc.). Offer safe spaces for input.
2: HCBS System Assessment
Review available data (NCI, SAMS, claims, etc.) regarding eligibility, assessment, person-centered-plan development, and HCBS delivery. Collect other data as recommended by the TA contractor.
Map current eligibility, assessment, person-centered plan development, and service system.
Assess the extent to which current benefit structures meet the needs of program participants. For example, delivery of HCBS vs rehab services.
Assess workforce capacity using tool(s) and strategies recommended by the TA contractor.
Inventory all care coordination/case management and assessment activities across AHS programs.
3: Establish New Eligibility, Assessment, Person-Centered-Plan Development, and Service Delivery Systems
Determine desired assessor and case manager qualifications, roles, and responsibilities.
Establish target caseload for assessors/case managers by program.
DECISION POINT: Impact analysis of independent assessment/case management options: should assessment or case mgmt be provided by the State, or procure for these services?
4: Reimbursement Methodologies and Financial Modeling
Assess financial impact of delivering assessment or case management via the State vs procure for these services.
Revise existing reimbursement methodologies/rates and value-based payment models based on new scope of work.
Establish reimbursement methodology for new assessment and/or case management entity(ies).
5: Statute, Policy, and Manual Review and Updating
Identify necessary statute changes and amend statutes.
Identify necessary rule changes and amend rules.
Identify necessary manual changes and amend manuals.
6: Quality Management System
Develop provider standards that address quality and performance measures for assessment and case management entities.
Develop quality review protocol for new assessment and case management entities. Modify quality review protocols for current service providers as needed.
Modify critical incident reporting (CIR) protocols.
7: Implementation Planning
Health care system integration planning.
Determine how, when, and which individuals will be transitioned to independent case management for assessment and person-centered planning.
Develop process flows for eligibility, assessments and reassessments, case management, service coordination, and service delivery.
Develop training and orientation plan for providers, assessors, case managers, consumers, families, advocates, community partners, etc.
As needed, establish a policy to identify areas of the state or scenarios that may be eligible for the only willing and qualified provider exemption.
Develop and execute selection process (e.g., request for proposals, certification process, provider enrollment, etc.) for entity(ies) to conducting assessments and/or case management.
Develop readiness review plan.
8: Implement New Eligibility, Assessment, Person-Centered-Plan Development, and Service Delivery Systems
Conduct readiness review
Update MMIS based on new billing/reimbursement structures, quality, and financial reporting.
Provide training and orientation to providers, assessors, case managers, consumers, families, advocates, community partners, etc.
Transition individuals to new assessment and case management system(s).

## 2023 Timeline
| Jan. 2023 | Feb. 2023 | Mar. 2023 | April 2023 | May 2023 | June 2023 | July 2023 | Aug. 2023 | Sept. 2023 | Oct. 2023 | Nov. 2023 | Dec. 2023
1: Stakeholder Engagement
Develop stakeholder engagement plan that maps out key internal and external stakeholders and when/how each stakeholder will be involved.
Establish advisory stakeholder group(s) consisting of consumers, providers, families, guardians, advocates, and other groups. Convene regularly for input/working sessions and regular updates.
Develop and provide diverse and accessible methods of informing/engaging stakeholders (webinars, letters, brochures, surveys, interviews, regional meetings etc.). Offer safe spaces for input.
2: HCBS System Assessment
Review available data (NCI, SAMS, claims, etc.) regarding eligibility, assessment, person-centered-plan development, and HCBS delivery. Collect other data as recommended by the TA contractor.
Map current eligibility, assessment, person-centered plan development, and service system.
Assess the extent to which current benefit structures meet the needs of program participants. For example, delivery of HCBS vs rehab services.
Assess workforce capacity using tool(s) and strategies recommended by the TA contractor.
Inventory all care coordination/case management and assessment activities across AHS programs.
3: Establish New Eligibility, Assessment, Person-Centered-Plan Development, and Service Delivery Systems
Determine desired assessor and case manager qualifications, roles, and responsibilities.
Establish target caseload for assessors/case managers by program.
DECISION POINT: Impact analysis of independent assessment/case management options: should assessment or case mgmt be provided by the State, or procure for these services?
4: Reimbursement Methodologies and Financial Modeling
Assess financial impact of delivering assessment or case management via the State vs procure for these services.
Revise existing reimbursement methodologies/rates and value-based payment models based on new scope of work.
Establish reimbursement methodology for new assessment and/or case management entity(ies).
5: Statute, Policy, and Manual Review and Updating
Identify necessary statute changes and amend statutes.
Identify necessary rule changes and amend rules.
Identify necessary manual changes and amend manuals.
6: Quality Management System
Develop provider standards that address quality and performance measures for assessment and case management entities.
Develop quality review protocol for new assessment and case management entities. Modify quality review protocols for current service providers as needed.
Modify critical incident reporting (CIR) protocols.
7: Implementation Planning
Health care system integration planning.
Determine how, when, and which individuals will be transitioned to independent case management for assessment and person-centered planning.
Develop process flows for eligibility, assessments and reassessments, case management, service coordination, and service delivery.
Develop training and orientation plan for providers, assessors, case managers, consumers, families, advocates, community partners, etc.
As needed, establish a policy to identify areas of the state or scenarios that may be eligible for the only willing and qualified provider exemption.
Develop and execute selection process (e.g., request for proposals, certification process, provider enrollment, etc.) for entity(ies) to conducting assessments and/or case management.
Develop readiness review plan.
8: Implement New Eligibility, Assessment, Person-Centered-Plan Development, and Service Delivery Systems
Conduct readiness review
Update MMIS based on new billing/reimbursement structures, quality, and financial reporting.
Provide training and orientation to providers, assessors, case managers, consumers, families, advocates, community partners, etc.
Transition individuals to new assessment and case management system(s).

## 2024 Timeline
| Jan. 2024 | Feb. 2024 | Mar. 2024 | April 2024 | May 2024 | June 2024 | July 2024 | Aug. 2024 | Sept. 2024 | Oct. 2024 | Nov. 2024 | Dec. 2024
1: Stakeholder Engagement
Develop stakeholder engagement plan that maps out key internal and external stakeholders and when/how each stakeholder will be involved.
Establish advisory stakeholder group(s) consisting of consumers, providers, families, guardians, advocates, and other groups. Convene regularly for input/working sessions and regular updates.
Develop and provide diverse and accessible methods of informing/engaging stakeholders (webinars, letters, brochures, surveys, interviews, regional meetings etc.). Offer safe spaces for input.
2: HCBS System Assessment
Review available data (NCI, SAMS, claims, etc.) regarding eligibility, assessment, person-centered-plan development, and HCBS delivery. Collect other data as recommended by the TA contractor.
Map current eligibility, assessment, person-centered plan development, and service system.
Assess the extent to which current benefit structures meet the needs of program participants. For example, delivery of HCBS vs rehab services.
Assess workforce capacity using tool(s) and strategies recommended by the TA contractor.
Inventory all care coordination/case management and assessment activities across AHS programs.
3: Establish New Eligibility, Assessment, Person-Centered-Plan Development, and Service Delivery Systems
Determine desired assessor and case manager qualifications, roles, and responsibilities.
Establish target caseload for assessors/case managers by program.
DECISION POINT: Impact analysis of independent assessment/case management options: should assessment or case mgmt be provided by the State, or procure for these services?
4: Reimbursement Methodologies and Financial Modeling
Assess financial impact of delivering assessment or case management via the State vs procure for these services.
Revise existing reimbursement methodologies/rates and value-based payment models based on new scope of work.
Establish reimbursement methodology for new assessment and/or case management entity(ies).
5: Statute, Policy, and Manual Review and Updating
Identify necessary statute changes and amend statutes.
Identify necessary rule changes and amend rules.
Identify necessary manual changes and amend manuals.
6: Quality Management System
Develop provider standards that address quality and performance measures for assessment and case management entities.
Develop quality review protocol for new assessment and case management entities. Modify quality review protocols for current service providers as needed.
Modify critical incident reporting (CIR) protocols.
7: Implementation Planning
Health care system integration planning.
Determine how, when, and which individuals will be transitioned to independent case management for assessment and person-centered planning.
Develop process flows for eligibility, assessments and reassessments, case management, service coordination, and service delivery.
Develop training and orientation plan for providers, assessors, case managers, consumers, families, advocates, community partners, etc.
As needed, establish a policy to identify areas of the state or scenarios that may be eligible for the only willing and qualified provider exemption.
Develop and execute selection process (e.g., request for proposals, certification process, provider enrollment, etc.) for entity(ies) to conducting assessments and/or case management.
Develop readiness review plan.
8: Implement New Eligibility, Assessment, Person-Centered-Plan Development, and Service Delivery Systems
Conduct readiness review
Update MMIS based on new billing/reimbursement structures, quality, and financial reporting.
Provide training and orientation to providers, assessors, case managers, consumers, families, advocates, community partners, etc.
Transition individuals to new assessment and case management system(s).

## 2025 Timeline
| Jan. 2025 | Feb. 2025 | Mar. 2025 | April 2025 | May 2025 | June 2025 | July 2025 | Aug. 2025 | Sept. 2025 | Oct. 2025 | Nov. 2025 | Dec. 2025
1: Stakeholder Engagement
Develop stakeholder engagement plan that maps out key internal and external stakeholders and when/how each stakeholder will be involved.
Establish advisory stakeholder group(s) consisting of consumers, providers, families, guardians, advocates, and other groups. Convene regularly for input/working sessions and regular updates.
Develop and provide diverse and accessible methods of informing/engaging stakeholders (webinars, letters, brochures, surveys, interviews, regional meetings etc.). Offer safe spaces for input.
2: HCBS System Assessment
Review available data (NCI, SAMS, claims, etc.) regarding eligibility, assessment, person-centered-plan development, and HCBS delivery. Collect other data as recommended by the TA contractor.
Map current eligibility, assessment, person-centered plan development, and service system.
Assess the extent to which current benefit structures meet the needs of program participants. For example, delivery of HCBS vs rehab services.
Assess workforce capacity using tool(s) and strategies recommended by the TA contractor.
Inventory all care coordination/case management and assessment activities across AHS programs.
3: Establish New Eligibility, Assessment, Person-Centered-Plan Development, and Service Delivery Systems
Determine desired assessor and case manager qualifications, roles, and responsibilities.
Establish target caseload for assessors/case managers by program.
DECISION POINT: Impact analysis of independent assessment/case management options: should assessment or case mgmt be provided by the State, or procure for these services?
4: Reimbursement Methodologies and Financial Modeling
Assess financial impact of delivering assessment or case management via the State vs procure for these services.
Revise existing reimbursement methodologies/rates and value-based payment models based on new scope of work.
Establish reimbursement methodology for new assessment and/or case management entity(ies).
5: Statute, Policy, and Manual Review and Updating
Identify necessary statute changes and amend statutes.
Identify necessary rule changes and amend rules.
Identify necessary manual changes and amend manuals.
6: Quality Management System
Develop provider standards that address quality and performance measures for assessment and case management entities.
Develop quality review protocol for new assessment and case management entities. Modify quality review protocols for current service providers as needed.
Modify critical incident reporting (CIR) protocols.
7: Implementation Planning
Health care system integration planning.
Determine how, when, and which individuals will be transitioned to independent case management for assessment and person-centered planning.
Develop process flows for eligibility, assessments and reassessments, case management, service coordination, and service delivery.
Develop training and orientation plan for providers, assessors, case managers, consumers, families, advocates, community partners, etc.
As needed, establish a policy to identify areas of the state or scenarios that may be eligible for the only willing and qualified provider exemption.
Develop and execute selection process (e.g., request for proposals, certification process, provider enrollment, etc.) for entity(ies) to conducting assessments and/or case management.
Develop readiness review plan.
8: Implement New Eligibility, Assessment, Person-Centered-Plan Development, and Service Delivery Systems
Conduct readiness review
Update MMIS based on new billing/reimbursement structures, quality, and financial reporting.
Provide training and orientation to providers, assessors, case managers, consumers, families, advocates, community partners, etc.
Transition individuals to new assessment and case management system(s).